## Slide 1
COST SUMMARY
Indicative · AED · ex-VAT · Option A: Azure UAE North
AED 2.58 M
Total one-time CAPEX
Infra + Licences + Application Dev
AED 629 K
Annual OPEX (Year 1)
Includes 12-month warranty & support
AED 2.01 M
Application development
1,095 person-days across 4 months
Cost category | Amount (AED) | Type | Detail
Infrastructure CAPEX (Option A) | 335,500 | One-time | see breakdown
Software Licences (Year 1) | 235,200 | One-time | see breakdown
Application development (M1–M4) | 2,007,000 | One-time | split M1–2 / M3–4
Total one-time CAPEX | 2,577,700 | — | —
Annual OPEX (Option A) | 629,200 | Recurring | see breakdown
Blended day rates: Architect AED 2,200 · Senior Developer 1,800 · Mid Developer 1,500 · QA / DevOps 1,400. The next four slides break each category down line-by-line.
IRETP — Technical Presentation
1 / 7

## Slide 2
INFRASTRUCTURE CAPEX
One-time setup · costed across three hosting options
Infrastructure item | Option A — Azure UAE North | Option B — On-Premises | Option C — Hybrid
Compute · App Service / VMs (3 hosts) | 48,000 | 320,000 | 220,000
SQL Server (managed / licensed) | 36,000 | 180,000 | 120,000
Redis cache cluster | 18,000 | 85,000 | 18,000
Azure AI Search / vector index | 24,000 | 65,000 | 24,000
Microsoft Fabric / OneLake lakehouse | 42,000 | 200,000 | 42,000
Blob Storage / on-prem NAS | 12,000 | 55,000 | 35,000
WAF + Front Door / on-prem F5 | 30,000 | 140,000 | 95,000
CDN (public static assets) | 8,000 | 25,000 | 12,000
Private endpoints + site-to-site network | 14,000 | 60,000 | 45,000
DR · cross-region replication (≤ 4 h RPO) | 28,000 | 180,000 | 95,000
SSL certificates (wildcard, 3-year) | 4,500 | 4,500 | 4,500
Monitoring · telemetry (Azure Monitor / Seq) | 16,000 | 45,000 | 28,000
Initial security hardening + pen-test | 55,000 | 55,000 | 55,000
Subtotal (AED) | 335,500 | 1,414,500 | 793,500
DLD selects the hosting model at contract signature; the rest of the financials adjust accordingly. AI inference and personal data remain UAE-resident on any option.
IRETP — Technical Presentation
2 / 7

## Slide 3
SOFTWARE LICENCES · SUBSCRIPTIONS
Year-1 stack · open-source components excluded
Licence / Subscription | Vendor | Unit cost (AED) | Qty | Annual (AED)
.NET 9 runtime + ASP.NET Core | Microsoft | Open-source | — | 0
Visual Studio Enterprise (dev seats) | Microsoft | 12,800 / seat / yr | 5 | 64,000
Hangfire Pro | HangfireIO | 7,200 / server / yr | 2 | 14,400
Azure OpenAI Service (tokens) | Microsoft | Consumption-based | — | 90,000 est.
AI fallback model (Anthropic API) | Anthropic | Consumption-based | — | 40,000 est.
SMTP relay (SendGrid / Postmark) | Twilio / Postmark | 2,400 / yr | 1 | 2,400
SMS gateway (UAE operator) | Operator | Per-message | — | 18,000 est.
PDF generation (QuestPDF) | QuestPDF | 2,800 / yr | 1 | 2,800
Seq log server (cloud) | Datalust | 3,600 / yr | 1 | 3,600
Subtotal (Year 1) | — | — | — | 235,200
Token-priced AI usage will be re-tiered at contract based on agreed monthly volume; estimate above sized on internal traffic projections.
IRETP — Technical Presentation
3 / 7

## Slide 4
APPLICATION DEVELOPMENT · MONTHS 1–2
Phase 1 + Phase 2 deliverables · effort and cost
Deliverable | Month | Effort (PD) | Cost (AED)
External Public Portal (CMS · Dashboard · Transactions · Map · Indices) | M1 · P1 | 120 | 216,000
Bilingual EN/AR · RTL · i18n pipeline | M1 · P1 | 40 | 72,000
Slice & Dice Analytics engine | M1 · P1 | 60 | 108,000
Real Estate AI Agent (Orchestrator · RAG · guardrails) | M1 · P1 | 100 | 180,000
Investor Notifications (email / SMS / in-platform) | M1 · P1 | 60 | 108,000
Open Data API · Developer Portal · API-key management | M1 · P1 | 50 | 90,000
Perf hardening · Redis cache · EF tuning | M1 · P1 | 30 | 54,000
Phase 1 QA · UAT support | M1 · P1 | 30 | 54,000
Phase 1 subtotal | M1 | 490 | 882,000
Watchlist v2 · ESG · GRETI sub-index tracker | M2 · P2 | 80 | 144,000
Analytics enhancements · saved views · embed | M2 · P2 | 40 | 72,000
Performance hardening · OpenTelemetry · load-test sign-off | M2 · P2 | 30 | 54,000
Phase 2 QA · UAT | M2 · P2 | 20 | 36,000
Phase 2 subtotal | M2 | 170 | 306,000
M1 + M2 cumulative | M1–M2 | 660 | 1,188,000
M1 is the heaviest spend — the External Portal and AI Agent stack land in the first month and underpin every later phase.
IRETP — Technical Presentation
4 / 7

## Slide 5
APPLICATION DEVELOPMENT · MONTHS 3–4
Phase 3 + Phase 4 deliverables · effort and cost
Deliverable | Month | Effort (PD) | Cost (AED)
EWRS (risk engine · L1–L4 escalation · dashboard · playbooks) | M3 · P3 | 100 | 180,000
Developer Performance & Rating + Escrow Monitoring | M3 · P3 | 80 | 144,000
Beneficial Ownership · Mortgage analytics · Name Validation | M3 · P3 | 40 | 72,000
DESC ISR v3 hardening + VAPT (external consultant) | M3 · P3 | 30 | 90,000
Phase 3 QA · UAT · security acceptance | M3 · P3 | 25 | 45,000
Phase 3 subtotal | M3 | 275 | 531,000
Multilingual extension (ZH · RU · UR · FR · HI · DE) + AI multi-language | M4 · P4 | 90 | 162,000
Advanced analytics · AI fine-tuning pipeline | M4 · P4 | 50 | 90,000
Phase 4 QA · UAT · language acceptance | M4 · P4 | 20 | 36,000
Phase 4 subtotal | M4 | 160 | 288,000
Total application development (M1–M4) | M1–M4 | 1,095 | 2,007,000
Phase 3 carries the DESC-authorised VAPT engagement (external consultant, AED 90 K embedded in the line item) — clean report required before Phase 3 UAT sign-off.
IRETP — Technical Presentation
5 / 7

## Slide 6
ANNUAL OPEX
Year-1 recurring · three hosting options
OPEX item | Option A — Azure UAE | Option B — On-Premises | Option C — Hybrid
Compute · VM · App Service | 48,000 | 85,000 | 75,000
SQL Server (managed annual) | 36,000 | 24,000 | 28,000
Redis · caching annual | 18,000 | 12,000 | 18,000
AI model API consumption (annual est.) | 130,000 | 130,000 | 130,000
OneLake · Fabric storage & compute | 42,000 | 68,000 | 42,000
Monitoring & SIEM | 16,000 | 28,000 | 22,000
SMTP · SMS channels | 20,400 | 20,400 | 20,400
Software licences (annual renewal) | 84,800 | 84,800 | 84,800
Warranty & support (12-mo post go-live) | 180,000 | 180,000 | 180,000
Security patching · monthly scans | 36,000 | 36,000 | 36,000
Data quality · reconciliation tooling | 18,000 | 18,000 | 18,000
Annual OPEX (Year 1) | 629,200 | 686,200 | 654,200
OPEX starts the month after go-live. Warranty & support pricing applies to all three hosting options at parity.
IRETP — Technical Presentation
6 / 7

## Slide 7
PAYMENT MILESTONES
Pay on UAT sign-off · 6 gates across 4 months
M0
Contract signature
10 %
AED 200,700
M1
Week 1 — mobilisation complete (infrastructure live · team onboard)
10 %
AED 200,700
M2
End of Month 1 — Phase 1 UAT sign-off (External Portal · AI Agent · Open Data)
25 %
AED 501,750
M3
End of Month 2 — Phase 2 UAT sign-off (ESG · GRETI · Analytics v2)
15 %
AED 301,050
M4
End of Month 3 — Phase 3 UAT sign-off (EWRS · Dev Rating · Escrow · VAPT clean)
25 %
AED 501,750
M5
End of Month 4 — Phase 4 UAT sign-off (Multilingual · Advanced Analytics)
15 %
AED 301,050
100 % of AED 2,007,000 development CAPEX is conditional on DLD-signed acceptance certificates.
IRETP — Technical Presentation
7 / 7