Dubai Land Department

RFP No. DLD-IRETP-2026-001

Financial Proposal

Integrated Real Estate Transparency Platform (IRETP) — RFP DLD-IRETP-2026-001 Response, Volume 3 of 3

| Programme | Integrated Real Estate Transparency Platform (IRETP) |
| --- | --- |
| Document Date | May 2026 |
| Classification | Confidential — Vendor Proposal |

# 1. Preamble & Disclaimer

All costs in this document are indicative ranges based on current market rates (UAE region, May 2026). Final binding figures will be provided in the vendor's official bid submission. All amounts are in UAE Dirhams (AED) exclusive of VAT. VAT at 5 % will be added to the final invoices. The cost structure follows the format mandated by RFP §14.

# 2. Executive Cost Summary

| Cost Category | Amount (AED) |
| --- | --- |
| Infrastructure CAPEX (Option A — Azure UAE North) | AED 335,500 |
| Software Licences CAPEX (first year) | AED 235,200 |
| Application Development CAPEX (all phases) | AED 2,007,000 |
| TOTAL ONE-TIME CAPEX | AED 2,577,700 |
| Annual OPEX (Option A — Azure UAE North) | AED 629,200 |
| Annual OPEX (Option B — On-Premises) | AED 686,200 |
| Annual OPEX (Option C — Hybrid) | AED 629,200 |

Hosting model selection Infrastructure CAPEX and annual OPEX differ by hosting option. Option A (Azure UAE North) is recommended for fastest time-to-production, built-in BCDR and lowest CAPEX. Option B (On-Premises) has higher CAPEX but may be preferred for data-sovereignty assurance. Option C (Hybrid) balances both objectives. DLD selects the model at contract signature and the financial schedules below are adjusted accordingly.

# 3. Infrastructure & Hosting Setup Costs (RFP §14.1 — One-Time CAPEX)

The table below covers all hosting components required to support the three application hosts (IRETP.WebAPI, IRETP.AdminAPI, IRETP.Web), the OneLake lakehouse, Redis cache, WAF, DR replication and security monitoring — across the three hosting options.

| Infrastructure Item | Option A: Azure UAE North | Option B: On-Premises | Option C: Hybrid |
| --- | --- | --- | --- |
| Compute — App Service Plan / VMs (3 hosts) | AED 48,000 | AED 320,000 | AED 48,000 |
| SQL Server managed / licensed | AED 36,000 | AED 180,000 | AED 36,000 |
| Redis Cache cluster | AED 18,000 | AED 85,000 | AED 18,000 |
| Azure AI Search / vector index | AED 24,000 | AED 65,000 | AED 24,000 |
| Microsoft Fabric / OneLake lakehouse tier | AED 42,000 | AED 200,000 | AED 42,000 |
| Azure Blob Storage / on-prem NAS (assets/export) | AED 12,000 | AED 55,000 | AED 12,000 |
| WAF + Front Door / on-prem F5 | AED 30,000 | AED 140,000 | AED 30,000 |
| CDN (public static assets) | AED 8,000 | AED 25,000 | AED 8,000 |
| Private endpoints / network config | AED 14,000 | AED 60,000 | AED 14,000 |
| DR / secondary-region replication (≤ 4 h RPO) | AED 28,000 | AED 180,000 | AED 28,000 |
| SSL certificates (wildcard, 3 yr) | AED 4,500 | AED 4,500 | AED 4,500 |
| Monitoring & telemetry (Azure Monitor / Seq) | AED 16,000 | AED 45,000 | AED 16,000 |
| Initial security hardening & penetration test | AED 55,000 | AED 55,000 | AED 55,000 |
| TOTAL INFRA CAPEX (indicative) | AED 335,500 | AED 1,414,500 | AED 335,500 |

# 4. Software Licences & Subscriptions (RFP §14.2 — First Year)

Licences required for the platform's first year of operation. Open-source components (MIT/Apache 2) carry no licence cost. AI model API costs are estimated at current token pricing and will be adjusted at contract based on agreed usage tiers.

| Licence / Subscription | Vendor | Unit Cost (AED) | Qty | Annual Cost (AED) |
| --- | --- | --- | --- | --- |
| .NET 8 runtime + ASP.NET Core | Microsoft | Open-source / included | — | AED 0 |
| Visual Studio Enterprise (dev seats) | Microsoft | AED 12,800 / seat / yr | 5 | AED 64,000 |
| Hangfire Pro | HangfireIO | AED 7,200 / server / yr | 2 | AED 14,400 |
| Azure OpenAI Service (tokens) | Microsoft | Consumption-based | — | AED 90,000 est. |
| AI fallback model (Anthropic API) | Anthropic | Consumption-based | — | AED 40,000 est. |
| SMTP relay (SendGrid / Postmark) | Twilio/Postmark | AED 2,400 / yr | 1 | AED 2,400 |
| SMS gateway (UAE operator) | Operator | Per-message | — | AED 18,000 est. |
| PDF generation library (QuestPDF) | QuestPDF | AED 2,800 / yr | 1 | AED 2,800 |
| Seq log server (cloud) | Datalust | AED 3,600 / yr | 1 | AED 3,600 |
| TOTAL SW LICENCES (indicative) |  |  |  | AED 235,200 |

# 5. Application Development & Implementation (RFP §14.3 — By Phase)

Development costs are broken down by phase gate deliverable. Rates are based on UAE-market blended day rates: Architect AED 2,200/day, Senior Developer AED 1,800/day, Mid Developer AED 1,500/day, QA/DevOps AED 1,400/day.

| Deliverable | Phase | Duration | Effort (person-days) | Cost (AED) |
| --- | --- | --- | --- | --- |
| External Public Portal (CMS, Dashboard, Transactions, Map, PriceIndex, RentalIndex) | P1 | M1–3 | 120 | AED 216,000 |
| Bilingual EN/AR RTL + i18n resource pipeline | P1 | M1–2 | 40 | AED 72,000 |
| Slice & Dice Analytics Engine | P1 | M2–3 | 60 | AED 108,000 |
| Real Estate AI Agent (AIOrchestrator, RAG, guardrails, Admin/AIModels) | P1 | M2–4 | 100 | AED 180,000 |
| Investor Notification & Alert System (email/SMS/in-platform) | P1 | M3–4 | 60 | AED 108,000 |
| Open Data API + Developer Portal + API key management | P1 | M4–5 | 50 | AED 90,000 |
| Performance hardening (Redis cache, caching behavior, EF tuning) | P1 | M5–6 | 30 | AED 54,000 |
| Phase 1 QA, UAT support, security review | P1 | M6 | 30 | AED 54,000 |
| PHASE 1 SUBTOTAL | P1 | M1–6 | 490 | AED 882,000 |
| Watchlist v2, ESG indicators, GRETI sub-index tracker | P2 | M6–8 | 80 | AED 144,000 |
| Analytics enhancements, saved-view sharing, embed improvements | P2 | M7–8 | 40 | AED 72,000 |
| Performance hardening (load-testing P95 sign-off, OpenTelemetry) | P2 | M8–9 | 30 | AED 54,000 |
| Phase 2 QA & UAT | P2 | M9 | 20 | AED 36,000 |
| PHASE 2 SUBTOTAL | P2 | M6–9 | 170 | AED 306,000 |
| EWRS (risk engine, escalation L1–L4, dashboard, playbooks) | P3 | M9–10 | 100 | AED 180,000 |
| Developer Performance & Rating + Escrow Monitoring | P3 | M10–11 | 80 | AED 144,000 |
| Beneficial Ownership, Mortgage Analytics, Name Validation | P3 | M11 | 40 | AED 72,000 |
| DESC ISR v3 hardening + VAPT (external consultant) | P3 | M11–12 | 30 | AED 90,000 |
| Phase 3 QA, UAT, security acceptance | P3 | M12 | 25 | AED 45,000 |
| PHASE 3 SUBTOTAL | P3 | M9–12 | 275 | AED 531,000 |
| Multilingual extension (ZH, RU, UR, FR, HI, DE) + AI multi-language | P4 | M12–14 | 90 | AED 162,000 |
| Advanced analytics, AI fine-tuning pipeline | P4 | M13–14 | 50 | AED 90,000 |
| Phase 4 QA, UAT, language acceptance | P4 | M15 | 20 | AED 36,000 |
| PHASE 4 SUBTOTAL | P4 | M12–15 | 160 | AED 288,000 |
| TOTAL DEVELOPMENT CAPEX | P1–P4 | M1–15 | 1,095 | AED 2,007,000 |

# 6. Annual Recurring Costs (RFP §14.4 — OPEX)

Annual operating costs including hosting, AI model consumption, software renewals, notification channels, monitoring, security scanning and the 12-month post-go-live warranty & support package.

| OPEX Item | Option A: Azure UAE | Option B: On-Premises | Option C: Hybrid |
| --- | --- | --- | --- |
| Compute / VM / App Service (annual) | AED 48,000 | AED 85,000 | AED 48,000 |
| SQL Server managed annual | AED 36,000 | AED 24,000 | AED 36,000 |
| Redis / caching annual | AED 18,000 | AED 12,000 | AED 18,000 |
| AI model API consumption (annual est.) | AED 130,000 | AED 130,000 | AED 130,000 |
| OneLake / Fabric storage & compute | AED 42,000 | AED 68,000 | AED 42,000 |
| Monitoring & SIEM | AED 16,000 | AED 28,000 | AED 16,000 |
| SMTP / SMS channels | AED 20,400 | AED 20,400 | AED 20,400 |
| Software licences (annual renewal) | AED 84,800 | AED 84,800 | AED 84,800 |
| Warranty & support (12 months post go-live) | AED 180,000 | AED 180,000 | AED 180,000 |
| Security patching & monthly pen-test scans | AED 36,000 | AED 36,000 | AED 36,000 |
| Data quality & reconciliation tooling | AED 18,000 | AED 18,000 | AED 18,000 |
| TOTAL ANNUAL OPEX (indicative) | AED 629,200 | AED 686,200 | AED 629,200 |

# 7. Payment Milestone Schedule

Payments are tied to DLD-signed acceptance certificates at each phase gate, ensuring the vendor is financially motivated to deliver on time and to the acceptance criteria defined in RFP §17.

| Milestone | Trigger Event | % of Dev CAPEX | Amount (AED) |
| --- | --- | --- | --- |
| M0 | Contract signature | 10 % | AED 200,700 |
| M1 | Phase 1 mobilisation complete (infrastructure live, team onboard) | 10 % | AED 200,700 |
| M2 | Phase 1 UAT sign-off (External Portal + AI Agent + Open Data API) | 25 % | AED 501,750 |
| M3 | Phase 2 UAT sign-off (ESG, GRETI, Analytics v2) | 15 % | AED 301,050 |
| M4 | Phase 3 UAT sign-off (EWRS, Developer Rating, Escrow; VAPT clean) | 25 % | AED 501,750 |
| M5 | Phase 4 UAT sign-off (Multilingual + Advanced Analytics) | 15 % | AED 301,050 |
|  | TOTAL DEVELOPMENT CAPEX (AED) | 100 % | AED 2,007,000 |

# 8. Value-Add Items (Included at No Extra Charge)

The 15 engineering improvements listed in the Technical Proposal (§18) — MediatR validation behavior, global exception handler, Redis caching, domain events, outbox pattern, SignalR hub, AI streaming, Polly resilience, Hangfire idempotency, OpenTelemetry, health checks, security headers, architecture tests, CI/CD pipelines, resource-based authorization — are included within the Phase 1 development budget and carry no additional line cost.

Value delivered At the indicative total CAPEX of AED 2,577,700 (Option A), DLD receives a production-ready, enterprise-grade IRETP platform that satisfies every clause of the RFP, with 15 additional engineering commitments that protect the platform's long-term operability — all within a phase-gated, pay-on-acceptance payment model.